## Sheet1
Activity | Duration | Resources | Predecessors | Resources per unit cost | crash duration | crash cost | deadline | Cost per Unit of resource1 | Cost per Unit of resource2 | Cost per Unit of resource5
A | 5 | resource2:2 | none | 30 | 2 | 50 | 7 | 50 | 40 | 60
B | 3 | resource1:1 | A | 20 | 1 | 60 | 4 | 50 | 40 | 60
C | 8 | resource5:5 | A,B | 50 | 3 | 90 | 10 | 50 | 40 | 60